# WWC SV Data Science Meeting Notes

March 4, 2016

Attending: Dung, Alexandra, Karin, Josine, Anna, Anu

### Agenda

- Retrospective on February talk. Modifications to event planning guidelines?

- Status update on March talk.

- Status update on Hadoop workshop.

- Status update on April and May talks.

- Status update on Josine’s group emails.

- How to coordinate with Women in Big Data Meetup group. (See email from Erin.)

- Resources page

- February event

  - Matt says it’s okay to use VMWare on a regular basis, probably once a month. We should check first to see if someone else in WWC is the primary contact for Matt. Josine will do when she talks to Guiti and Snehil about hosting process; include Dung on communications.

  - Added a few details to planning guidelines.

- March event

  - Sarah and Anu are not on this call; they will be having a meeting early next week.

  - The host has asked when the meetup will be posted; Alexandra will follow up with Sarah and Anu next week to get details.

- Hadoop workshop

  - Alexandra has posted the Meetup. Need these details - need to commit to whole course? How much homework? Karin to continue to follow up with Shivva.

  - Alexandra to reduce cap to 25 people.

- April talk:

  - Silicon Valley Data Science confirmed for 4/21.

  - Silvia at SVDC to ask around to see if she has a speaker; if not, we’ll find someone.

- May talk:

  - H20 may be able to host and have speaker (Erin) - Anu has contacted her, but hasn’t heard back. Will follow up again.

- Shared document updates:

  - Data Science Tracking sheet has list of potential speakers in Activity Plans tab; we can add more possibilities there. Josine to make this a separate sheet.

  - Alexandra to update email list from last event.

- Josine’s updates:

  - Sent general newsletter as well as specific email to everyone who indicated they wanted to volunteer, along with a survey about what kind of volunteering they want to do.

  - Josine to have a call on 3/14 with at 5:30 with the three people who have volunteered to search for hosts. Will include Dung on this call.

  - ML and Kaggle workshop - three people at Meetup said they wanted to help organize, now have six people total. Call with them next Wednesday.

  - Will send next newsletter sometime before 3/23 talk. Can also include info about Hadoop workshop, any other workshops that have come together.

- Women in Big Data meetup - how to follow up on Erin’s emails.

  - Alexandra will talk with Elizabeth about ways to do cross postings and promote each other’s events. Dung will help out.

- Communication: seems to be working well with regular meetings, emails, and Google docs.

- Next call: Friday 3/11 5:00. Karin will send out invite.

Tabled topics:

- Discuss items to add to the pipeline; Anna's summary of our survey responses will be helpful to review here.

- Other goals for our group beyond meetups? There was some discussion last time about creating a data science resource list we can share with WWC members.