## Overview plan
Yellow = action needed
Event Date | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
1/13/2016, "Art of start", idea sharing, team selection, name selection, dividing shares/resposibilities? | Y | Guiti | Alaina Percival | alaina@womenwhocode.com | CEO, WWCode
| Y | Guiti | Ari Horie | ea@womenstartuplab.com | CEO, womenStartupLab
| Y | Guiti | Niousha Zadeh | niousha@gmail.com | CEO, britehealth
| Y | Ramesh | Shilpi Sharma | shilpi.sharma@kvantuminc.com | Founder&CEO, Kvantum
|  | Guiti |  | guiti.nabavi@gmail.com | moderator
|  | Mkting owner | Mkting Deadline | Marketing action
|  | Guiti | 2015-12-18 | flyer, writeup, list of Q to presenters, maybe website?
|  | Guiti | 2016-01-02 | Bay-Area-Dream-Chasers-Entrepreneurship-group-announce@meetup.com, drupal-group-list@meetup.com, WWCode-svleaders@googlegroups.com, ruby-99@meetup.com,TechinMotionSiliconValley-list@meetup.com, SVE-list@meetup.com, Svsian-list@meetup.com, CofounderClub-list@meetup.com, softwaredev-92@meetup.com
|  | Erin/Snehal | 2016-01-02 | Post to relevant Facebook groups, email leaders to post on their groups/tweet etc.: Pythonistas, Black Girls Code, Girl Develop It - SJ, PyLadies, Women in Big Data/Machine Learning, Design+Code etc.
|  | Ramesh | 2016-01-02 | ?Add all that applies, Post flyer to HDojo, email to meetup lists you are member of,
|  | Marina | 2015-12-19 | Post to Twitter; UXDI on FB; FemIgniters (LinkedIn); Connect, Work, Thrive (LinkedIn) - done
|  | Erin | ASAP | All fb, twitter, Instagram posts
March VHC | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
Even
2016-03-30 | Pending response | Erin/Snehal | Sramana Mitra | mkelly@bizbookpr.com | 1M / 1M Founder | http://www.sramanamitra.com/bio/ | Contacted, need to recontact with date
[6 empty] | http://femgineer.com/about/ | Any date after 15th May work for you? Say - 19,20,26 May? -Snehal
| ? | Guiti | Chuck Eesley | cee@stanford.edu | Prof: Stanford Tech Entrepreneur
|  | Marina | preliminary agreement from 1 female entrepreneur and 1 angel investor with a very solid legal background (Google), to be confirmed in January
|  | Mkting owner | Mkting Deadline | Marketing action | ***Must book by Feb 1 for all appropriate marketing to be on time***
|  |  | Event title | "StartedUp. Now what? legal or MVP" - March
|  | Snehal? |  | ? | moderator
|  | Snehal/Guiti | @ least 2-4 weeks before event | Meetup
|  | Erin | 2 weeks before event | Design of flyer?
|  | Erin / Dung | 2 weeks before event | Standard WWC-SV Social media push (fb, twitter, insta)
|  | Erin / Snehal |  | Email draft
May VHC | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
May TBD, MVP or prototype | Pending specific date | Erin/Snehal | Poornima | poornima@femgineer.com | CEO, Femingeer |  | Karin and Poornima co-authored a book together
| Pending specific date | Erin/Snehal | Karin Caitlin |  |  |  | g
|  | ? |  | ? | moderator
|  | Mkting owner | Mkting Deadline | Marketing action
Event Date | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
July TBD, Fundraising
|  | Mkting owner | Mkting Deadline | Marketing action
Event Date | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
|  | Mkting owner | Mkting Deadline | Marketing action
Event Date | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
|  | Mkting owner | Mkting Deadline | Marketing action
Event Date | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes

## Execution March
Planned Date | Actual Date | Status | Task | Volunteer | Notes
2016-01-13 |  | Complete | Date of previous event
1/18/2016 |  | Complete | Meeting #1 | Group
1/20/2016 |  | Not Started | Upload video of previous event | Guiti | Guiti will edit the video and post it
1/22/2016 |  | Not Started | Post previous event outcomes/material on FB or other sites
1/18/2016 |  | Complete | Finalize next event date | Group | March 30th
1/18/2016 |  | In Progress | Finalize topic for next event | Group | Ideation, Idea to MVP?
|  | Not Started | Determine tag line for next event | Group
|  | Complete | Finalize location | Group | Dojo
|  | Complete | Finalize # of speakers | Group | 3
|  | Complete | Finalize duration of event | Group | Event is usually 2 hrs. 1/2 hr of networking. 1:15 min event and 15 min of photos or more networking
|  | Complete | Determine moderator | Group | Snehal
|  | In Progress | Book room (event location) | Ramesh
|  | Not Started | Finalize meeting #2 Date
|  | In Progress | Meeting #1 notes |  | Multiple ideas discussed for topics eg: How to setup a business, market research ideas, idea to MVP. Need to finalize the vision/mission, should it be only a women only event or open to both men and women, how is it different frm start up grind etc
1/28/2016 |  | Not Started | Meeting #2 - discuss and finalize speakers
|  | Not Started | Identify Speaker #1
|  | Not Started | Identify Speaker #2
|  | Not Started | Identify Speaker #3
Identify team and volunteers for event

## Overview Template
Yellow = action needed
Event Date | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
1/13/2016, "Art of start", idea sharing, team selection, name selection, dividing shares/resposibilities? | Y | Guiti | Alaina Percival | alaina@womenwhocode.com | CEO, WWCode
| Y | Guiti | Ari Horie | ea@womenstartuplab.com | CEO, womenStartupLab
| Y | Guiti | Niousha Zadeh | niousha@gmail.com | CEO, britehealth
| Y | Ramesh | Shilpi Sharma | shilpi.sharma@kvantuminc.com | Founder&CEO, Kvantum
|  | Guiti |  | guiti.nabavi@gmail.com | moderator
|  | Mkting owner | Mkting Deadline | Marketing action
|  | Guiti | 2015-12-18 | flyer, writeup, list of Q to presenters, maybe website?
|  | Guiti | 2016-01-02 | Post to 3 meetup groups: drupal-group-list@meetup.com, WWCode-sv, SVE-list@meetup.com, Svsian-list@meetup.com, CofounderClub-list@meetup.com, softwaredev-92@meetup.com
|  | Erin/Snehal | 2016-01-02 | Post to relevant Facebook groups, email leaders to post on their groups/tweet etc.: Pythonistas, Black Girls Code, Girl Develop It - SJ, PyLadies, Women in Big Data/Machine Learning, Design+Code etc.
|  | Ramesh | 2016-01-02 | ?Add all that applies, Post flyer to HDojo, email to meetup lists you are member of,
|  | Marina | 2015-12-19 | Post to Twitter; UXDI on FB; FemIgniters (LinkedIn); Connect, Work, Thrive (LinkedIn) - done
|  | Erin | ASAP | All fb, twitter, Instagram posts
March VHC | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
March, "StartedUp. Now what? legal or MVP" - DATE??? April 1 / March 31 | ? | Erin/Snehal | Sramana Mitra | mkelly@bizbookpr.com | 1M / 1M Founder | http://www.sramanamitra.com/bio/ | Contacted, need to recontact with date
| ? | Erin/Snehal | Poornima | poornima@femgineer.com | CEO, Femingeer | http://femgineer.com/about/ | Any date after 15th May work for you? Say - 19,20,26 May? -Snehal
| ? | Guiti | Chuck Eesley | cee@stanford.edu | Prof: Stanford Tech Entrepreneur
|  | Marina | preliminary agreement from 1 female entrepreneur and 1 angel investor with a very solid legal background (Google), to be confirmed in January
|  | Mkting owner | Mkting Deadline | Marketing action | ***Must book by Feb 1 for all appropriate marketing to be on time***
|  | Snehal? |  | ? | moderator
|  | Snehal/Guiti | @ least 2-4 weeks before event | Meetup
|  | Erin | 2 weeks before event | Design of flyer?
|  | Erin / Dung | 2 weeks before event | Standard WWC-SV Social media push (fb, twitter, insta)
|  | Erin / Snehal |  | Email draft
May VHC | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
May TBD, MVP or prototype
|  | ? |  | ? | moderator
|  | Mkting owner | Mkting Deadline | Marketing action
Event Date | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
July TBD, Fundraising
|  | Mkting owner | Mkting Deadline | Marketing action
Event Date | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
|  | Mkting owner | Mkting Deadline | Marketing action
Event Date | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes
|  | Mkting owner | Mkting Deadline | Marketing action
Event Date | Booked (Y/N) | Lead | Speaker name, bio/site link | Speaker (or their assistant) contact info | speaker, title | person/site link | Notes

## Execution Template
Planned Date | Actual Date | Status | Task | Volunteer | Notes
X |  | Not Started | Date of previous event
#VALUE! |  | Not Started | Meeting #1
#VALUE! |  | Not Started | Upload video of previous event
#VALUE! |  | Not Started | Post previous event outcomes/material on FB or other sites
X |  | Not Started | Finalize next event date
#VALUE! |  | Not Started | Finalize topic for next event
|  | Not Started | Determine tag line for next event
|  | Not Started | Finalize location
|  | Not Started | Finalize # of speakers
|  | Not Started | Finalize duration of event |  | Event is usually 2 hrs. 1/2 hr of networking. 1:15 min event and 15 min of photos or more networking
|  | Not Started | Determine moderator
|  | Not Started | Book room (event location)
|  | Not Started | Finalize meeting #2 Date
|  | Not Started | Meeting #1 notes
#VALUE! |  | Not Started | Meeting #2 - discuss and finalize speakers
|  | Not Started | Identify Speaker #1
|  | Not Started | Identify Speaker #2
|  | Not Started | Identify Speaker #3
Identify team and volunteers for event